IF Factory Launch & Scheduling Plan — Executive Version

Official Launch Date: Monday, September 15, 2025
Initial Launch Window: 12 Weeks (thru December 6, 2025)
Creator Rollout: 500 creators in 5 cohorts of 100
Primary Objective: Validate the creator ecosystem, surface breakout IP, and position for Q1 2026 scale-up.

Phase 0: Final Prep & Infrastructure
Timeframe: August 18 – September 12, 2025
Executive Goal: Finalize Operational Backbone & Validate Systems with Beta Cohort

Week of August 18–22
- Complete staffing for leadership, production, analytics, and creator ops
- Finalize creator portal and backend analytics
- Soft launch: beta test with 15–20 creators across categories

Week of August 25–29
- Lock 100 creators for Cohort 1
- Prep studio/stage/office facilities (Lionsgate in-kind)
- Finish pre-launch content with beta/test creators

Week of September 1–12
- Final rehearsals, performance testing, and creative alignment
- Prepare marketing drops and social campaigns
- Host internal preview + Lionsgate exec walkthrough

Phase 1: Official Launch Week
Dates: September 15–21, 2025
Executive Goal: Establish Market Presence & Validate Initial Creator Pipeline

Monday, Sept 15:
- Global livestream event
- Drop 3–5 premiere short-form projects
- Activate press outreach

Sept 16–21:
- Onboard Cohort 1 (100 creators) — Target: 85% onboarding completion
- Daily drops of sizzle reels + creator intros
- Begin collecting core KPIs (views, shares, drop-off points, etc.)

Phase 2: Momentum & Expansion
Dates: Sept 22 – Oct 19, 2025
Executive Goal: Prove Scalable Onboarding + Initial Monetization Outcomes

- Onboard Cohort 2–5 (100 creators per week)
- Launch “Creator Spotlight” weekly series
- Pilot monetization models: ads, tipping, paid episodes
- Roll out “IP Boost Fund” to amplify top-performing content
- Start proactive press cycles on emerging breakout talent

Phase 3: Breakout Acceleration
Dates: Oct 20 – Nov 16, 2025
Executive Goal: Surface & Package High-Value IP for Lionsgate Distribution

- Activate full 500-creator slate
- Weekly performance tiers and highlight reels
- Package top-performing projects into 3–5 IP bundles for distribution
- Begin outbound licensing convos with Lionsgate, FAST channels, and third parties
- Drop first branded content pilots with external partners

Phase 4: Closeout & Investor Activation
Dates: Nov 17 – Dec 6, 2025
Executive Goal: Quantify ROI, Secure Phase 2 Capital, and Lock Distribution Deals

- Host IF Demo Day for Lionsgate execs and strategic investors
- Present: Creator case studies, ROI projections, performance dashboard
- Finalize at least 3 IP packages for Q1 2026
- Announce Phase 2 Expansion Plan (target: 2,000 creators by April 2026)
- Drop “Zero to Hero” mini-doc series to amplify platform success

Core Operational Disciplines (Ongoing)

Data & Growth
- Weekly: Creator performance dashboards + breakout scouting
- Monthly: Monetization progress reports & fan behavior trends

Talent & Creative
- Biweekly: Format testing + creator feedback loop
- Continuous: Studio coaching + IP equity onboarding

Stakeholder Engagement
- Monthly: Stakeholder video briefings + pitch updates
- Quarterly: Capital strategy reviews + licensing health check